## M3 Documents
Documentation/Output | Phases.Activity.Task | Phase 0 Readiness | Phase 1 Readiness | Phase 2 Selection | Phase 3 Engagement | Phase 4 Migration | Phase 5 Operations
Vision Statement | 0.1.3 | Version 1
In-Scope Service Area(s) and Function(s) | 0.1.4,0.1.5,0.1.6 | Version 1
Expected Benefits | 0.1.9 | Version 1
High Level Timelines | 0.1.10 | Version 1
Investment Readiness Checklist | 0,1 | Version 1 | Updated
Project Business Case | 0,1 | Version 1 | Updated
Program Charter | 1,3 |  | Version 1 |  | Updated
Resource Management Plan | 1,2,3,4 |  | Version 1 | Updated | Updated | Updated
Program Management Plan | 1,2,3,4 |  | Version 1 | Updated | Updated | Updated
Initial Master Schedule | 1,2 |  | Version 1 | Updated
Independent Verification & Validation (IV&V) Plan | 1,2,3,4 |  | Version 1 | Updated | Updated | Updated
Status Reports/Dashboards | 1,2,3,4 |  | Version 1 | Updated | Updated | Updated
Governance Plan | 1,3 |  | Version 1 |  | Updated
Risk Management Plan | 1,2,3,4 |  | Version 1 | Updated | Updated | Updated
Risk, Actions, Issues, and Decisions (RAID) Log | 1,2,3,4 |  | Version 1 | Updated | Updated | Updated
M3 Risk Assessment Tool | 1,2,3,4 |  | Version 1 | Updated | Updated | Updated
Acquisition Strategy | 1,2 |  | Version 1 | Updated
Quality Assurance Surveillance Plan (QASP) | 1,3 |  | Version 1 |  | Updated
Life Cycle Cost Estimate (LCCE) | 1 |  | Version 1 | Updated
Baseline and Target Performance and Success Metrics | 1 |  | Version 1
Stakeholder Analysis | 1 |  | Version 1
Communications Plan | 1,2,3,4,5 |  | Version 1 | Updated | Updated | Updated | Updated
Migration and Operations and Maintenance (O&M) training needs | 1 |  | Version 1
As-Is Workforce Documentation | 1 |  | Version 1
As-Is Systems Environment | 1,3 |  | Version 1 |  | Updated
Target State Systems Environment | 1,3 |  | Version 1 |  | Updated
Data Governance Model | 1 |  | Version 1
Data Cleansing Plan | 1,2,3 |  | Version 1 | Updated | Updated
Target State Concept of Operations | 1,3 |  | Version 1 |  | Updated
Requirements Management Plan | 1,3 |  | Version 1 |  | Updated
Business Needs Workbook | 1,2 |  | Version 1 | Updated
Business Capabilities | 1 |  | Version 1
Implementation Approach/Schedule | 2 |  |  | Version 1
Cost Estimates | 2 |  |  | Version 1
Provider Assessment Report (Federal Only) | 2 |  |  | Version 1
Provider Agreement (IAA, if Federal) | 2 |  |  | Version 1
Draft Request for Proposal (RFP) (Commercial Only) | 2 |  |  | Version 1
Labor Relations Strategy | 2,3,4 |  |  | Version 1 | Updated | Updated
Change Management Plan | 1,2,3,4,5 |  | Version 1 | Updated | Updated | Updated | Updated
Change Readiness Assessment | 1,2,3,4 |  | Version 1 | Updated | Updated | Updated
Data Cleansing Scripts | 2,3 |  |  | Version 1 | Updated
Decommission Plan | 2,3,4, 5 |  |  | Version 1 | Updated | Updated | Updated
Business Process Reengineering Strategy | 2,4 |  |  | Version 1 |  | Updated
Validated As-Is Process Maps | 2 |  |  | Version 1
Change Request Log | 3,4,5 |  |  |  | Version 1 | Updated | Updated
Change Request Form | 3,4 |  |  |  | Version 1 | Updated
Integrated Master Schedule (IMS) | 3 |  |  |  | Version 1
Lessons Learned Report | 3,5 |  |  |  | Version 1 |  | Updated
Migration Approach, including Technical Strategies | 3 |  |  |  | Version 1
Go/No-Go Criteria for Go-Live Assessment | 3,4 |  |  |  | Version 1 | Updated
Business Readiness Assessment | 1 |  | Version 1
Workforce Assessment | 1,3,4 |  | Version 1 |  | Updated | Updated
Training Plan | 3,4,5 |  |  |  | Version 1 | Updated | Updated
Requirements Traceability Matrix (RTM) | 3,4 |  |  |  | Version 1 | Updated
Requirements Fit Gap Analysis | 3 |  |  |  | Version 1
Validated and Updated As-Is Systems Environment | 3 |  |  |  | Version 1
Test Plan | 3,4 |  |  |  | Version 1 | Updated
Configuration Management Plan | 3 |  |  |  | Version 1
CooP and Disaster Recovery Plan | 3 |  |  |  | Version 1
Interface Strategy | 3 |  |  |  | Version 1
Enhancement Strategy | 3 |  |  |  | Version 1
Documented Data Structure and Mapping | 3 |  |  |  | Version 1
Data Conversion Plan | 3,4 |  |  |  | Version 1 | Updated
Contact Center Strategy | 3 |  |  |  | Version 1
Service Level Agreements (SLAs) | 3,5 |  |  |  | Version 1 |  | Updated
O&M Governance Plan | 4,5 |  |  |  |  | Version 1 | Updated
Contingency Plan | 4 |  |  |  |  | Version 1
Go/No-Go Readiness Criteria | 4 |  |  |  |  | Version 1
Go/No-Go Assessment Report | 4 |  |  |  |  | Version 1
Target State Organization Design | 4 |  |  |  |  | Version 1
Workforce Transition Strategy | 4 |  |  |  |  | Version 1
Targeted Cutover Communications Plan | 4 |  |  |  |  | Version 1
Training Materials | 4,5 |  |  |  |  | Version 1 | Updated
Training Evaluations | 4,5 |  |  |  |  | Version 1 | Updated
Security Documentation, including Security Test Results and ATO | 4 |  |  |  |  | Version 1
Privacy Documentation, including Initial Privacy Assessment, FIPS 199, System of Records Notice (SORN), Privacy Impact Assessment | 4 |  |  |  |  | Version 1
Baselined List of ID Credentials | 4 |  |  |  |  | Version 1
Configuration Workbooks | 4 |  |  |  |  | Version 1
Interface Control Document | 4 |  |  |  |  | Version 1
Reports Design Document | 4 |  |  |  |  | Version 1
Mock Conversion Report | 4 |  |  |  |  | Version 1
Test Scripts | 4 |  |  |  |  | Version 1
Test Results Report | 4 |  |  |  |  | Version 1
Test Defect Log | 4 |  |  |  |  | Version 1
Cutover Plan | 4,5 |  |  |  |  | Version 1 | Updated
Target State Process Flows | 4,5 |  |  |  |  | Version 1 | Updated
Standard Operating Procedures (SOPs) | 4,5 |  |  |  |  | Version 1 | Updated
Final Report on Success Metrics | 5 | [5 empty] | Version 1
Lessons Learned Questionnaire | 5 | [5 empty] | Version 1
SLA Performance Reports | 5 | [5 empty] | Version 1
Completed Training Evaluations | 5 | [5 empty] | Version 1
Communications Materials | 5 | [5 empty] | Version 1
Post Implementation and Evaluation Report | 5 | [5 empty] | Version 1
Decommission Report | 5 | [5 empty] | Version 1

## Examples on Max.gov
Phase | Example Title | Agency
0 | Exception Business Case_DOJ_6.2016_ | DOJ
0 | Vision, As-Is Workforce Documentation and Initial Target State Systems Environment_HUD_12.2015_ | HUD
0 | Vision_Commerce_12.2015_ | Commerce
0 | Vision_HUD_12.2014_ | HUD
0 | Embarking On Shared Services - Business Case Analysis Strategies Tools | GSA
1 | TFM OCM _ Initial Stakeholder Interview Report_FINAL | OPM
1 | As Is Systems Environment_GSA_ 06.2016_ | GSA
1 | As Is Systems Environment_GSA_08.2016_ | GSA
1 | As-Is Systems Architecture_NSF_03.2018 | NSF
1 | As-Is Workforce Documentation and Initial Target State Systems Environment_DOL_06.2017 | DOL
1 | As-Is Workforce Documentation and Initial Target State Systems Environment_VA_02.2017 | VA
1 | As-Is Workforce Documentation_GSA_04.2016 | GSA
1 | Business Capabilities_NSF_03.2018 | NSF
1 | Change Readiness Assessment_GSA_06.2015 | GSA
1 | Common Business Capabilities_GSA_08.2016 | GSA
1 | Change Readiness Assessment_GSA_06.2015 | GSA
1 | Common Business Capabilities_GSA_08.2016 | GSA
1 | Communications Plan_GSA_08.2016 | GSA
1 | Copy of Change Readiness Assessment_GSA_06.2015 | GSA
1 | Copy of Data Cleansing Plan_GSA_08.2016Version1 | GSA
1 | Data Cleansing Plan_GSA_08.2016Version1 | GSA
1 | Data Governance Model_GSA_05.2016Version1 | GSA
1 | Data Governance Model_GSA_05.2016Version2 | GSA
1 | Exception Business Case_04.2016_GSA_4 of 4 | GSA
1 | Exception Business Case_DOJ_06.2016 | DOJ
1 | Exception Business Case_GSA_07.2015_2 of 4 | GSA
1 | Exception Business Case_GSA_11.2015_1 of 4 | GSA
1 | Exception Business Case_GSA_11.2015_3 of 4 | GSA
1 | Existing Data Quality Assessments_NSF_03.2018 | NSF
1 | Governance Charter_DOL_12.2016 | DOL
1 | Governance Model_GSA_08.2016 | GSA
1 | HR Staffing Plan IPT Structure_GSA_08.2016 | GSA
1 | HR Staffing Plan Org Structure_GSA_08.2016Version1 | GSA
1 | Independent Verification and Validation Plan_GSA_08.2016 | GSA
1 | Initial Scope of Services_GSA_.07 | GSA
1 | Initial Target State Systems Environment_GSA_07.2016 | GSA
1 | Life Cycle Cost Estimate_GSA_10.2017 | GSA
1 | Life Cycle Cost Estimate_NSF_03.2018 | NSF
1 | M3 Risk Assessment_GSA_10.2017 | GSA
1 | Migration and Operations and Maintenance Training Needs_GSA_07.2016 | GSA
1 | Phase 1 Tollgate Review_DOL_06.2017 | DOL
1 | Phase 1 Tollgate Review_GSA_09.2016 | GSA
1 | Phase 1 Tollgate Review_VA_02.2017 | VA
1 | Procurement Plan_GSA_08.2016 | GSA
1 | Procurement Plan_VA_12.2016 | VA
1 | Program Management Plan_GSA_12.2016 | GSA
1 | Quality Assurance Surveillance Plan_GSA_07 | GSA
1 | Requirements Management Plan_GSA_08.2016 | GSA
1 | Risk Action Issue Decision Log_GSA_08.2016Version1 | GSA
1 | Risk Management Plan_GSA_08.2016 | GSA
1 | Stakeholder Analysis_GSA_08.2016 | GSA
1 | Target Performance and Success Metrics_GSA_11.2015 | GSA
1 | Target Performance and Success Metrics_NSF_03.2018 | NSF
1 | Unique Business Capabilities_GSA_06.2016 | GSA
1 | Validated As-Is Process Maps_GSA_08.2016Version2 | GSA
1 | Validated As-Is Process Maps_GSA_2014Version1 | GSA
1 | Vision, As-Is Workforce Documentation and Initial Target State Systems Environment_HUD_12.2015 | HUD
1 | 2018 0826 TFM Acquisition Strategy V1 | OPM
1 | 2019 0118 TFM Program Charter v1.0 | OPM
1 | 2020 0428 TFM ESC Charter v2.0 | OPM
1 | 2021 0520 TFM OCM Plan_Final | OPM
1 | 2021 0310 TFM Program Management Plan v2 | OPM
1 | 2021 0322 TFM Communications Management Plan v1.2 | OPM
1 | 2021 0430 TFM Action Items Tracker | OPM
1 | 2021 0430 TFM Risk Register | OPM
1 | OPM TFM FFS – Replacement_Project_Charter_20201209 | OPM
1 | 2021 0430 TFM Decisions Tracker | OPM
1 | Life Cycle Cost Estimate_NSF_03.2018 | NSF
2 | Business Process Reengineering Strategy_NSF_09.2015 | NSF
2 | Change Management Plan_DOJ_11.2016 | DOJ
2 | Change Management Plan_GSA_08.2017Version2 | GSA
2 | Change Management Plan_GSA_09.2017Version3 | GSA
2 | Communications Plan_DOJ_10.2016 | DOJ
2 | Copy of Business Process Reengineering Strategy_NSF_09.2015 | NSF
2 | Engagement and Fit-Gap Analysis | VA
2 | Engagement and Fit-Gap Analysis_VA_07.2018 | VA
2 | Engagement, Fit-Gap Analysis, Business Process Reengineering_VA_02.2017Version1 | VA
2 | Engagement, Fit-Gap Analysis, Business Process Reengineering_VA_02.2017Version2 | VA
2 | Exception Business Case_04.2016_GSA_4 of 4 | GSA
2 | Exception Business Case_DOJ_06.2016 | DOJ
2 | Exception Business Case_GSA_07.2015_2 of 4 | GSA
2 | Exception Business Case_GSA_11.2015_1 of 4 | GSA
2 | Exception Business Case_GSA_11.2015_3 of 4 | GSA
2 | Governance Charter_VA_04.2016 | VA
2 | HR Staffing Plan_DOJ_08.2016 | DOJ
2 | HR Staffing Plan_VA_07.2016 | VA
2 | Implementation Approach Schedule_DOJ | DOJ
2 | Independent Verification and Validation Plan_VA_10.2016 | VA
2 | Labor Relations Strategy Draft_GSA_08.2017 | GSA
2 | Life Cycle Cost Estimate_VA_01 | VA
2 | M3 Risk Assessment_GSA_10.2017 | GSA
2 | Master Schedule_DOJ_02.2017 | DOJ
2 | Master Schedule_VA_10.2016 | VA
2 | Phase 2 Tollgate Review_VA_02.2017 | VA
2 | Program Health Assessment_VA_05.2017 | VA
2 | Program Management Plan_GSA_12.2016 | GSA
2 | RFQ WITH Supplemental Docs_NSF_03.2018 | NSF
2 | RFQ_GSA_.07 | GSA
2 | RFQ_NSF_03.2018 | NSF
2 | Risk Management Plan_VA_07.2016 | VA
2 | Statement of Work_NSF_03.2018 | NSF
2 | Target State Concept of Operations_DOJ_01.2017 | DOJ
2 | Weekly Schedule Status Update Report_VA_03.2017 | VA
3 | Business Process Reengineering_VA_02.2017 | VA
3 | Change Management Plan_GSA_09.2017Version4 | GSA
3 | Communications Plan_GSA_05.2017Version2 | GSA
3 | Contact Center Strategy_GSA_10.2017 | GSA
3 | Copy of 3 of 4_Exception Business Case_GSA_11.2015 | GSA
3 | Data Cleansing Plan_GSA_10.2017Version2 | GSA
3 | Fit Gap Analysis_GSA_05.2017 | GSA
3 | Fit Gap Analysis_VA_02.2017 | VA
3 | HR Staffing Plan Org Structure_GSA_10.2017Version2 | GSA
3 | Independent Verification and Validation Plan_GSA_05.2017Version2 | GSA
3 | Life Cycle Cost Estimate_NSF_03.2018 | NSF
3 | M3 Risk Assessment_GSA_10.2017 | GSA
3 | Master Schedule_DOL_01.2017 | DOL
3 | Master Schedule_GSA_01.2017 | GSA
3 | Migration Approach, including Technical Strategies_GSA_05.2017 | GSA
3 | Migration Approach_DOJ_10.2016 | DOJ
3 | Migration Approach_HUD_11.2015 | HUD
3 | Procurement Plan_GSA_10.2017 | GSA
3 | Procurement Plan_NSF_03.2018 | NSF
3 | Procurement Strategy_VA_12.2016 | VA
3 | Program Management Plan_GSA_12.2016 | GSA
3 | Risk Action Issue Decision Log_GSA_10.2017Version2 | GSA
3 | RTM from Fit Gap Analysis_GSA_05.2017 | GSA
3 | Scope of Services_GSA_11.2016 | GSA
3 | Service Level Agreement_NSF_03.2018 | NSF
3 | Target State Concept of Operations_DOJ_01.2017 | DOJ
3 | Target State Systems Environment Integrated_GSA_07.2017 | GSA
3 | Target State Systems Environment_GSA_09.2017 | GSA
3 | Validated and Updated As Is Systems Environment_GSA_07.2015 | GSA
3 | 2021 0401 TFM IMS – FFSR Detail Report | OPM
3 | OFM FFS – Replacement_Requirements Management Plan_20201215 | OPM
4 | Business Process Reengineering Strategy_NSF_09.2015 | NSF
4 | Go No-Go Assessment Report_DOJ_10.2017 | DOJ
4 | Go No-Go Assessment Report_HUD_08.2015 | HUD
4 | Go No-Go Readiness Criteria for Go-Live_DOJ_10.2017 | DOJ
4 | Life Cycle Cost Estimate_NSF_03.2018 | NSF
4 | M3 Risk Assessment_GSA_10.2017 | GSA
4 | Program Management Plan_GSA_12.2016 | GSA
4 | Service Level Agreement_NSF_03.2018 | NSF
4 | 2021 0401 TFM IMS – Migration Critical Report | OPM
4 | 2021 0401 TFM IMS – TFM Late and Upcoming Tasks | OPM
4 | 2021 0430 TFM Artifacts Tracker | OPM
5 | Lessons Learned Report_GSA_10.2017 | GSA
5 | Program Management Plan_GSA_12.2016 | GSA
5 | 2021 0323 TFM Quarterly Lessons Learned Report FINAL | OPM