## Slide 1: Phase 4 Progress Review Discussion Template
GSA, Office of Shared Solutions and Performance Improvement
Month, Year

## Slide 2: Questions to be Answered
This template is intended to guide a Progress Review discussion between a Customer, Provider and Key Stakeholders.
4. Migration
Questions to Be Answered | 
 | Are there still gaps between common business requirements? Are they warranted?
 | What is the level of confidence in the comprehensive risk assessment of the health of the project to identify major challenges and a mitigation strategy? Is the provider adequately prepared and resourced to deploy the solution and support the customer during O&M? Is the customer adequately prepared and resourced to go-live and operate during O&M? Are adequate plans in place to address known issues that will arise during O&M?
 | If there are changes to the total migration cost, are they reasonable? Current/future budget impact?
 | Does the effort align with each office initiative?

## Slide 3: Instructions for Completing This Template
This template is intended to guide a Progress Review discussion between a Customer, Provider and Key Stakeholders.
To use this template:
Use the source documents included within each slide to develop summary-level information that will help guide the Progress Review
Be prepared to discuss specific questions/content included on each slide before or during the Progress Review
Once complete, schedule a Progress Review meeting

## Slide 4: Documentation Required for Phase 4 Progress Review
The following documentation is required in guiding a discussion to demonstrate readiness and gain approval for Phase 4. Agencies purchasing transaction processing services only will identify relevant activities and artifacts for their project using the M3 Services Tailoring Guide.
Exit Criteria (to move into Phase 5) | 
Go/No-Go Criteria Met | 
Information Contained in Progress Review Discussion | 
Business Operations Readiness Criteria Tasks and Status Contingency Plan Data Conversion Results M3 Risk Assessment Tool Organizational Readiness Criteria Tasks and Status Program Management Readiness Criteria Tasks and Status Risk and Issues Summary Technology Readiness Criteria Tasks and Status Test Results | 
Phase 4 Documentation | 
Baselined List of ID Credentials Business Process Reengineering Strategy Change Management Plan Change Readiness Assessment Change Request Form Change Request Log Communications Plan Configuration Management Plan Configuration Workbooks Contingency Plan Conversion Defect Log Cutover Plan Data Conversion Plan Decommission Plan Desk Guides/User Guide Go/No-Go Assessment Report Go/No-Go Readiness Criteria Independent Verification & Validation (IV&V) Plan Integrated Master Schedule (IMS) Interface Control Document Labor Relations Strategy M3 Risk Assessment Tool Mock Conversion Report O&M Governance Plan Privacy Documentation | Program Management Plan Resource Management Plan Reports Design Document Requirements Traceability Matrix (RTM) Risk Management Plan Risks, Actions, Issues, and Decisions (RAID) Log Security Documentation Standard Operating Procedures Status Reports/Dashboards Target State Organization Design Target State Process Flows Target State Process Maps Targeted Cutover Communications Plan Test Defect Log Test Plan •Test Results Report Target State Concept of Operations Test Scripts Training Evaluations Training Materials Training Plan Workforce Assessment Workforce Transition Strategy

## Slide 5: M3 Risk Assessment Tool
Determine the risk rating during Phase 4 using the M3 Risk Assessment Tool and submit with progress review material.
ILLUSTRATIVE

## Slide 6: Overview of Go/No-Go Decision Making Process
Describe the process for assessing the program’s readiness per the criteria identified
Readiness Categories
Program Management: Program Management processes have been defined and are being followed
Technology: Migration activities have been completed successfully and are ready for deployment
Organizational: Human Capital components of the program are ready for end users to adopt new systems and processes
Business Operations: Processes, infrastructure, and controls are in place for operational environment
Source Documentation from Playbook
Go/No-Go Readiness Criteria

## Slide 7: Health Indicator Definitions and Criticality Matrix
Reference the Criticality/Health Indicator Matrix and definitions below to complete the Readiness Category Health Indicator Summary
Category | Criticality Definitions
Approval | All high criticality tasks meet success criteria; any medium and low tasks that have not met success criteria contain documented issues and corresponding, detailed action plans for resolution by deployment
Approval Denied | One or more high criticality tasks has not met the success criteria and are not expected to be complete by deployment, and/or the program/organization has open risks / issues that must be resolved before it can be considered operationally ready
Category | Health Indicator Definitions
Green | Successfully completed or on track to be successfully completed according to IMS with minimal risk
Yellow | Risk identified with mitigation plan documented and being tracked towards resolution for deployment
Red | Risk identified with no mitigation plan in place OR not on track to be resolved for deployment
 |  | Health Indicator Ratings (count) |  |  | 
 |  | Green | Yellow | Red | TOTAL
Criticality Rating | High |  |  |  | 
 | Medium |  |  |  | 
 | Low |  |  |  | 
 | TOTAL |  |  |  | 
Source Documentation from Playbook
RAID log Go/No-Go Readiness Criteria
Category | Criticality Definitions
High | Greater than 10% impact to budget, critical path milestones impacted, cannot meet program milestones
Medium | Greater than 5% and less than 10% impact budget, no impact to milestones
Low | Less than 1% impact to budget, no impact to schedule, no impact on ability to meet key dates

## Slide 8: Readiness Category Health Indicator Summary
Provide the status of each task/artifact in each of the readiness categories listed below
 |  | Health Indicator Ratings (count) |  |  | 
 |  | Green | Yellow | Red | TOTAL
Criticality Rating | High |  |  |  | 
 | Medium |  |  |  | 
 | Low |  |  |  | 
 | TOTAL |  |  |  | 
Program Management Readiness
Technology Readiness
Business Operations Readiness
Organizational Readiness
 |  | Health Indicator Ratings (count) |  |  | 
 |  | Green | Yellow | Red | TOTAL
Criticality Rating | High |  |  |  | 
 | Medium |  |  |  | 
 | Low |  |  |  | 
 | TOTAL |  |  |  | 
 |  | Health Indicator Ratings (count) |  |  | 
 |  | Green | Yellow | Red | TOTAL
Criticality Rating | High |  |  |  | 
 | Medium |  |  |  | 
 | Low |  |  |  | 
 | TOTAL |  |  |  | 
 |  | Health Indicator Ratings (count) |  |  | 
 |  | Green | Yellow | Red | TOTAL
Criticality Rating | High |  |  |  | 
 | Medium |  |  |  | 
 | Low |  |  |  | 
 | TOTAL |  |  |  | 
Source Documentation from Playbook
RAID log Go/No-Go Readiness Criteria

## Slide 9: Justification/Action Plan for Unmet Criteria
Provide additional justification or action plan to address readiness criteria that has been indicated as YELLOW or RED. Provide details of actions completed for items that were changed from yellow or red to GREEN
Readiness Category | No. | Task | Go / No-Go Success Criteria | Health Indicator | Justification / Action Plan
Program Management Readiness |  |  |  | Red | 
 |  |  |  | Yellow | 
Organizational Readiness |  |  |  | Yellow | 
 |  |  |  | Green | 
Technology Readiness |  |  |  | Yellow | 
 |  |  |  | Red | 
Business Operations Readiness |  |  |  | Yellow | 
 |  |  |  | Green | 
Source Documentation from Playbook
RAID log Go/No-Go Readiness Criteria

## Slide 10: Program Management Readiness Criteria Tasks and Status
Program Management Readiness
Organizational Readiness
Technology
Readiness
Business Operations Readiness
No | Task | Owner | Criticality | Go/No-Go Success Criteria | Health Indicator | Status
1. | Program Schedule/work breakdown structure (WBS): Are there any tasks that impact Go-Live that are late or at risk of becoming late? |  |  | All tasks impacting Go-Live are on schedule or contain less than 10% variance |  | 
2. | Risk/Issue Register: Have all High Severity risks/issues related to the program/release been closed or mitigated? |  |  | All risks have been documented and tracked and no High severity risks / issues remain without mitigation |  | 
3. | O&M Governance: Are post-implementation governance procedures in place? |  |  | Governance procedures have been defined and approved |  | 
 |  | Health Indicator Ratings (count) |  |  | 
 |  | Green | Yellow | Red | TOTAL
Criticality Rating | High |  |  |  | 
 | Medium |  |  |  | 
 | Low |  |  |  | 
 | TOTAL |  |  |  | 
Source Documentation from Playbook
RAID log Go/No-Go Readiness Criteria
Indicates additional summary slide required in presentation
The organization should tailor or add criteria based on the nature of the migration
Program Management Readiness
Organizational Readiness
Technology
Readiness
Business Operations Readiness
Business Operations Readiness
Program Management Readiness
Organizational Readiness
Technology
Readiness

## Slide 11: Program Management Readiness Criteria Tasks and Status
No | Task | Owner | Criticality | Go/No-Go Success Criteria | Health Indicator | Status
4. | Contingency Plan: Are all necessary implementation contingency plans in place for roll back procedures? |  |  | All contingency plans have been developed and approved |  | 
 | <Organization Defined> |  |  |  |  | 
 | <Organization Defined> |  |  |  |  | 
Source Documentation from Playbook
RAID log Go/No-Go Readiness Criteria Contingency Plan
Indicates additional summary slide required in presentation
Program Management Readiness
Organizational Readiness
Technology
Readiness
Business Operations Readiness

## Slide 12: Risk and Issue Summary
Please provide a summary of the risks and issues of the program
 |  | Risk Status (count) |  |  | 
 |  | Closed/ Cancelled | Deferred | In Progress | Grand Total
Risk Severity | High |  |  |  | 
 | Medium |  |  |  | 
 | Low |  |  |  | 
 | Grand Total |  |  |  | 
 |  | Issue Status (count) |  | 
 |  | Closed/ Cancelled | In Progress | Grand Total
Issue Priority | High |  |  | 
 | Medium |  |  | 
 | Low |  |  | 
 | Grand Total |  |  | 
Source Documentation from Playbook
RAID log

## Slide 13: Contingency Plan
Describe the contingency plan in place if a No-Go decision is made or if rollback procedures need to be executed
Describe impacts on systems, data, workforce, costs, and migration team
Source Documentation from Playbook
Contingency Plan

## Slide 14: Organizational Readiness Criteria Tasks and Status
 |  | Health Indicator Ratings (count) |  |  | 
 |  | Green | Yellow | Red | TOTAL
Criticality Rating | High |  |  |  | 
 | Medium |  |  |  | 
 | Low |  |  |  | 
 | TOTAL |  |  |  | 
Program Management Readiness
Organizational Readiness
Technology
Readiness
Business Operations Readiness
No | Task | Owner | Criticality | Go / No-Go Success Criteria | Health Indicator | Status
5. | Union Agreement: Are all union negotiations and agreements regarding testing and training complete? |  |  | Union agreements have met requirements of collective bargaining agreements for testing, training , and staffing |  | 
6. | Training Delivery: Have training materials been developed? Have training sessions been planned and scheduled for end users? |  |  | All training sessions have been planned and scheduled |  | 
7. | Target State Business Processes: Have the business process changes about retained organization been documented? |  |  | Business process changes have been documented |  | 
Source Documentation from Playbook
RAID log Readiness Assessment Go/No-Go Readiness Criteria

## Slide 15: Organizational Readiness Criteria Tasks and Status
No | Task | Owner | Criticality | Go/No-Go Success Criteria | Health Indicator | Status
8. | Communications Delivery: Have end user Go-Live communications on been drafted and scheduled? Have the future state process changes been communicated? |  |  | All communications have been planned, drafted, and delivered per the work plan |  | 
 | <Organization Defined> |  |  |  |  | 
 | <Organization Defined> |  |  |  |  | 
Program Management Readiness
Organizational Readiness
Technology
Readiness
Business Operations Readiness
Source Documentation from Playbook
RAID log Communications Plan Go/No-Go Readiness Criteria

## Slide 16: Technology Readiness Criteria Tasks and Status
 |  | Health Indicator Ratings (count) |  |  | 
 |  | Green | Yellow | Red | TOTAL
Criticality Rating | High |  |  |  | 
 | Medium |  |  |  | 
 | Low |  |  |  | 
 | TOTAL |  |  |  | 
No | Task | Owner | Criticality | Go / No-Go Success Criteria | Health Indicator | Status
9. | Baselined Requirements: Have all requirements been baselined and placed under change control? |  |  | All requirements have been baselined |  | 
10. | Account Code Structure and Data Mapping: Is the new structure defined and applied to relevant data (e.g., interfaces or data conversion)? |  |  | Account code structure and data mappings have been defined and approved |  | 
11. | Configuration Changes: Have all configuration changes been documented (e.g., updated master data tables)? |  |  | All configuration changes have been implemented and tested |  | 
Indicates additional summary slide required in presentation
Program Management Readiness
Organizational Readiness
Technology
Readiness
Business Operations Readiness
Source Documentation from Playbook
RAID log RTM Go/No-Go Readiness Criteria

## Slide 17: Technology Readiness Criteria Tasks and Status
No | Task | Owner | Criticality | Go / No-Go Success Criteria | Health Indicator | Status
12. | Interfaces: Have all interfaces been designed, developed, and tested? |  |  | No critical issues remain after mock data conversion or user acceptance testing |  | 
13. | Testing: Have all defects rated high or critical been closed? For those that remain open has a plan been established to address the requirement? |  |  | All test cases have been completed and assigned an outcome. For defects that remain open, a workaround has been developed and approved to meet the business requirement |  | 
14. | Data Conversion: Have all of the planned mock conversions been completed and met the exit criteria? |  |  | Mock conversions have been completed and meet the exit criteria |  | 
15. | Cutover Plan: Are all tasks identified in the cutover plan on track for completion? |  |  | No issues have been identified in cutover activities |  | 
16. | Change Management Log and Disposition: Have all change requests been tracked and dispositioned? |  |  | All change requests have been tracked and dispositioned |  | 
Indicates additional summary slide required in presentation
Program Management Readiness
Organizational Readiness
Technology
Readiness
Business Operations Readiness
Source Documentation from Playbook
RAID log Interface Control Document Test Results Reports Conversion Defect Log Change Request Log Go/No-Go Readiness Criteria

## Slide 18: Test Results
Summarize the test results, including number of scripts executed and passed and outstanding high priority defects that remain
Source Documentation from Playbook
Test Results Reports

## Slide 19: Conversion Results
Summarize the results of mock conversion of the number of records for conversion, percentage converted successfully, percentage not converted successfully, and outstanding high priority defects and issues that remain
Source Documentation from Playbook
Test Results Reports

## Slide 20: Business Operations Readiness Criteria Tasks and Status
 |  | Health Indicator Ratings (count) |  |  | 
 |  | Green | Yellow | Red | TOTAL
Criticality Rating | High |  |  |  | 
 | Medium |  |  |  | 
 | Low |  |  |  | 
 | TOTAL |  |  |  | 
No | Task | Owner | Criticality | Go / No-Go Success Criteria | Health Indicator | Status
17. | Customer Resource Readiness: Does Customer have resources in place and trained to perform O&M activities? Are contracts in place to supplement O&M resources? |  |  | Customer organization has required resources identified and trained to support O&M processes |  | 
18. | Provider Readiness: Does the provider have the people, facilities, equipment, training, and technology to support ongoing transaction processing based on anticipated volume? |  |  | Provider resources and infrastructure are in place to support expected transaction volumes |  | 
19. | O&M Contracts/Service Level Agreements (SLAs): Are the O&M contracts and SLAs defined and awarded? |  |  | O&M IAA and SLAs have been defined and awarded |  | 
Program Management Readiness
Organizational Readiness
Technology
Readiness
Business Operations Readiness
Source Documentation from Playbook
Service Level Agreements

## Slide 21: Business Operations Readiness Criteria Tasks and Status
No | Task | Owner | Criticality | Go/No-Go Success Criteria | Health Indicator | Status
20. | O&M Procedures: Have the O&M procedures been created? Are people in place to support these processes? |  |  | O&M procedures have been establish and individuals have been identified and trained to perform O&M support processes |  | 
21. | Help Desk: Have the Help Desk processes and procedures been defined? Is the provider Help Desk prepared for deployment? Do end users know how to access the help desk? |  |  | Help Desk procedures have been established and individuals have been identified and trained to perform duties; end users have been made aware of how to access the help desk |  | 
22. | Reporting: Have reports been designed and tested? |  |  | Reports have been tested |  | 
23. | System of Records Notice (SORN): Are all required notices in place? |  |  | SORNs have been approved for required applications |  | 
24. | Security Reviews/Authorization to Operate (ATO): Have all required security reviews, assessments, and approvals been completed and have any necessary ATO requests been received? |  |  | ATOs have been approved for custom development (if applicable) |  | 
Indicates additional summary slide required in presentation
Program Management Readiness
Organizational Readiness
Technology
Readiness
Business Operations Readiness
Source Documentation from Playbook
Security Documentation Service Level Agreements

## Slide 22: Business Operations Readiness Criteria Tasks and Status
No | Task | Owner | Criticality | Go/No-Go Success Criteria | Health Indicator | Status
25. | Business Continuity/Disaster Recovery: Are business continuity and disaster recovery plans defined and understood? |  |  | Business continuity and disaster recovery plans have been defined |  | 
26. | Personally Identifiable Information (PII): Are protocols in place to securely transfer PII? |  |  | PII protocols are in place |  | 
Program Management Readiness
Organizational Readiness
Technology
Readiness
Business Operations Readiness
Source Documentation from Playbook
Privacy Documentation Readiness Assessment

## Slide 23: Readiness Criteria Tasks and Status
No | Task | Owner | Criticality | Go/No-Go Success Criteria | Health Indicator | Status
 | <Organization Defined> |  |  |  |  | 
 | <Organization Defined> |  |  |  |  | 
Program Management Readiness
Organizational Readiness
Technology
Readiness
Business Operations Readiness

## Slide 24: Operations and Maintenance Procedures
Describe the O&M Procedures in place to manage both systems and services, including resources from the customer and provider to support procedures
Source Documentation from Playbook
Service Level Agreement

## Slide 25: Help Desk
Describe the help desk and customer care options available to end users for support and the escalation procedures in place for issue resolution
Source Documentation from Playbook
Service Level Agreement